## 1. Task Sheet
Tasks | Finish by | Leader | Supporters | Comments
First Prototype |  |  |  | The first prototype aims to realize the most basic functionality: 25 MHz differential output at 1W.
Design the PA circuit | End of October 2025 | Luis Wong | Jeremiah Dados
Design the EMG circuit | End of October 2025 | Dmytro Stavskyi | Jeremiah Dados
Design the first prototype PCB in Altium | Mid- November 2025 | Jeremiah Dados | Luis Wong, Dmytro Stavskyi
Place the fabrication order | Mid- November 2025 | Jeremiah Dados | Han Wu
Receive the board and assemble it | End of November 2025 | Jeremiah Dados | Luis Wong, Dmytro Stavskyi
Validate board outputs on lab equipment | Mid- December 2025 | Jeremiah Dados | Luis Wong, Dmytro Stavskyi | Present the functional prototype at the end of semester.
Validate board functionality in animal experiments | End of January 2026 | Han Wu | Jeremiah Dados, Luis Wong, Dmytro Stavskyi | Work resumes the second week of January after the winter break.
Second Prototype |  |  |  | The second prototype addresses the issues found in the first prototype and makes the device more compact and flexible.
Revisions to the circuit design | Mid-February 2026 | Luis Wong, Dmytro Stavskyi | Jeremiah Dados
Design and order the PCB | End of February 2026 | Jeremiah Dados | Luis Wong, Dmytro Stavskyi
Place the fabrication order | End of February 2026 | Jeremiah Dados | Han Wu
Receive the board and assemble it | Mid-March 2026 | Luis Wong, Dmytro Stavskyi | Jeremiah Dados
Validate board outputs on lab equipment | End of March 2026 | Jeremiah Dados | Luis Wong, Dmytro Stavskyi
Validate board functionality in animal experiments | End of April 2026 | Han Wu | Jeremiah Dados, Luis Wong, Dmytro Stavskyi

## Summary
Actual % Complete | 18.62%